## TZC Cost Position
G & T Cost Update - Rev 2 Dated 20/5/22 |  |  |  | RLF Cost Plan No. 2 |  | Mid Point Costs
Detailed Cost position (uninflated) |  |  |  | Detailed Cost position (uninflated) |  | Detailed Cost position (uninflated)
Element | Assumption |  |  | Element | Assumption | Element | Assumption
Environmental & Ecological Works | 701000 |  |  | Environmental & Ecological Works | 701000 | Environmental & Ecological Works | 701000
Demolition, Site Clearance & Land Formation | 893000 |  |  | Demolition, Site Clearance & Land Formation | 892000 | Demolition, Site Clearance & Land Formation | 892500
Onsite Roads | 6635000 |  |  | Onsite Roads | 5913000 | Onsite Roads | 6274000
Offsite Infrastructure | 195000 |  |  | Offsite Infrastructure | 101000 | Offsite Infrastructure | 148000
Utilities - Diversions | - |  |  | Utilities - Diversions | - | Utilities - Diversions | -
Utilities- Reinforcements | 1067000 |  |  | Utilities- Reinforcements | 1190000 | Utilities- Reinforcements | 1128500
Utilities - Onsite Distribution | 3937000 |  |  | Utilities - Onsite Distribution | 2599000 | Utilities - Onsite Distribution | 3268000
Surface Water Drainage | 1793000 |  |  | Surface Water Drainage | 935000 | Surface Water Drainage | 1364000
Foul Water Drainage | 1577000 |  |  | Foul Water Drainage | 783000 | Foul Water Drainage | 1180000
Public Realm | 2570000 |  |  | Public Realm | 2393000 | Public Realm | 2481500
Housing | 77038205 |  |  | Housing | 75148000 | Housing | 76093102.5
Parking | 1839750 |  |  | Parking | 1731000 | Parking | 1785375
Total | 98245955 |  |  | Total | 92386000 | Total | 95315977.5
Gross Internal Area | 474483
Summary cost position (uninflated) |  |  |  | Summary cost position (uninflated) |  | Summary cost position (uninflated)
House Building Total | 78877955 |  |  | House Building | 76879000 | House Building | 77878477.5
House Building Rate Per Sq ft | 166.2398 |  |  | House Building Rate Per Sq ft | 162.0269 | House Building Rate Per Sq ft | 164.1333
Infrastructure / Abnormals | 19368000 |  |  | Infrastructure / Abnormals | 15507000 | Infrastructure / Abnormals | 17437500
Total | 98245955 |  |  | Total | 92386000 | Total | 95315977.5
Inflation Calculation |  |  |  | Inflation Calculation |  | Inflation Calculation
Total build from cost plan | 102159939 |  |  | Total build from cost plan | 101624000
Inflation from cost plan | 3013719 |  |  | Inflation from cost plan | 2998000
Inflation rate from cost plan | 2.95% |  |  | Inflation rate from cost plan | 2.95% | Inflation rate from cost plan | 2.95%
Summary cost position (inflated) |  |  |  | Summary cost position (inflated) |  | Summary cost position (inflated)
House Building Total | 81204855.2898 |  |  | House Building Total | 79147000.0984 | House Building Total | 80175963.0895
House Building Rate Per Sq ft | 171.1439 |  |  | House Building Rate Per Sq ft | 166.8068 | House Building Rate Per Sq ft | 168.9754
Infrastructure / Abnormals | 19939356.1516 |  |  | Infrastructure / Abnormals | 15964470.5385 | Infrastructure / Abnormals | 17951922.0361
Total | 101144211.4414 |  |  | Total | 95111470.6369 | Total | 98127885.1256
Extra Carbon offset contribution |  |  |  | Extra Carbon offset contribution |  | Extra Carbon offset contribution
Extra carbon offset contribution to be absorbed in housing base build costs | 543600 |  |  | Extra carbon offset contribution to be absorbed in housing base build costs | 543600 | Extra carbon offset contribution to be absorbed in housing base build costs | 543600
Triple Glazing addition |  |  |  | Triple Glazing addition |  | Triple Glazing addition
Triple Point Glazing | 1617000 |  |  | Triple Point Glazing | 1617000 | Triple Point Glazing | 1617000
Total Cost position |  |  |  | Total Cost position |  | Total Cost position
House Building + Extra Carbon + Triple Glazing | 83365455.2898 |  |  | House Building + Extra Carbon | 81307600.0984 | House Building + Extra Carbon | 82336563.0895
House Building Rate Per Sq ft | 175.6975 |  |  | House Building Rate Per Sq ft | 171.3604 | House Building Rate Per Sq ft | 173.529
Infrastructure / Abnormals | 19939356.1516 |  |  | Infrastructure / Abnormals | 15964470.5385 | Infrastructure / Abnormals | 17951922.0361
Total | 103304987.1388 |  |  | Total | 97272241.9973 | Total | 100288658.6546
Summary position
| G & T Costs | RLF Costs | Mid Point Cost position
House Building | 83365455.2898 | 81307600.0984 | 82336563.0895
Infrastructure / Abnormals | 19939356.1516 | 15964470.5385 | 17951922.0361
Total | 103304811.4414 | 97272070.6369 | 100288485.1256
| 217.7208 | 205.0064 | 211.3637

## VE Cost Position.
G & T Cost Update - Rev 2 Dated 14/09/22 |  |  |  | RLF Cost Plan No. 2 |  | Mid Point Costs
Detailed Cost position (uninflated) |  |  |  | Detailed Cost position (uninflated) |  | Detailed Cost position (uninflated)
Element | Assumption |  |  | Element | Assumption | Element | Assumption
Environmental & Ecological Works | 701000 |  |  | Environmental & Ecological Works | 701000 | Environmental & Ecological Works | 701000
Demolition, Site Clearance & Land Formation | 893000 |  |  | Demolition, Site Clearance & Land Formation | 892000 | Demolition, Site Clearance & Land Formation | 892500
Onsite Roads | 6635000 |  |  | Onsite Roads | 5913000 | Onsite Roads | 6274000
Offsite Infrastructure | 195000 |  |  | Offsite Infrastructure | 101000 | Offsite Infrastructure | 148000
Utilities - Diversions | - |  |  | Utilities - Diversions | - | Utilities - Diversions | -
Utilities- Reinforcements | 1067000 |  |  | Utilities- Reinforcements | 1190000 | Utilities- Reinforcements | 1128500
Utilities - Onsite Distribution | 3937000 |  |  | Utilities - Onsite Distribution | 2599000 | Utilities - Onsite Distribution | 3268000
Surface Water Drainage | 1793000 |  |  | Surface Water Drainage | 935000 | Surface Water Drainage | 1364000
Foul Water Drainage | 1577000 |  |  | Foul Water Drainage | 783000 | Foul Water Drainage | 1180000
Public Realm | 2570000 |  |  | Public Realm | 2393000 | Public Realm | 2481500
Housing | 71664922 |  |  | Housing | 68620000 | Housing | 70142461
Parking | 1839750 |  |  | Parking | 1731000 | Parking | 1785375
Total | 92872672 |  |  | Total | 85858000 | Total | 89365336
Gross Internal Area | 474483
Summary cost position (uninflated) |  |  |  | Summary cost position (uninflated) |  | Summary cost position (uninflated)
House Building Total | 73504672 |  |  | House Building | 70351000 | House Building | 71927836
House Building Rate Per Sq ft | 154.9153 |  |  | House Building Rate Per Sq ft | 148.2687 | House Building Rate Per Sq ft | 151.592
Infrastructure / Abnormals | 19368000 |  |  | Infrastructure / Abnormals | 15507000 | Infrastructure / Abnormals | 17437500
Total | 92872672 |  |  | Total | 85858000 | Total | 89365336
Inflation Calculation |  |  |  | Inflation Calculation |  | Inflation Calculation
Total build from cost plan | 102159939 |  |  | Total build from cost plan | 101624000
Inflation from cost plan | 3013719 |  |  | Inflation from cost plan | 2998000
Inflation rate from cost plan | 2.95% |  |  | Inflation rate from cost plan | 2.95% | Inflation rate from cost plan | 2.95%
Summary cost position (inflated) |  |  |  | Summary cost position (inflated) |  | Summary cost position (inflated)
House Building Total | 75673060.3992 |  |  | House Building Total | 72426418.1886 | House Building Total | 74049772.2781
House Building Rate Per Sq ft | 159.4853 |  |  | House Building Rate Per Sq ft | 152.6428 | House Building Rate Per Sq ft | 156.0641
Infrastructure / Abnormals | 19939356.1516 |  |  | Infrastructure / Abnormals | 15964470.5385 | Infrastructure / Abnormals | 17951922.0361
Total | 95612416.5508 |  |  | Total | 88390888.7271 | Total | 92001694.3143
Extra Carbon offset contribution |  |  |  | Extra Carbon offset contribution |  | Extra Carbon offset contribution
Extra carbon offset contribution to be absorbed in housing base build costs | 543600 |  |  | Extra carbon offset contribution to be absorbed in housing base build costs | 543600 | Extra carbon offset contribution to be absorbed in housing base build costs | 543600
Triple Glazing addition |  |  |  | Triple Glazing addition |  | Triple Glazing addition
Triple Point Glazing | 1617000 |  |  | Triple Point Glazing | 1617000 | Triple Point Glazing | 1617000
Total Cost position |  |  |  | Total Cost position |  | Total Cost position
House Building + Extra Carbon + Triple Glazing | 77833660.3992 |  |  | House Building + Extra Carbon | 74587018.1886 | House Building + Extra Carbon | 76210372.2781
House Building Rate Per Sq ft | 164.0389 |  |  | House Building Rate Per Sq ft | 157.1964 | House Building Rate Per Sq ft | 160.6177
Infrastructure / Abnormals | 19939356.1516 |  |  | Infrastructure / Abnormals | 15964470.5385 | Infrastructure / Abnormals | 17951922.0361
Total | 97773180.5897 |  |  | Total | 90551645.9235 | Total | 94162454.932
Summary position
| G & T Costs | RLF Costs | Mid Point Cost position
House Building | 77833660.3992 | 74587018.1886 | 76210372.2781
Infrastructure / Abnormals | 19939356.1516 | 15964470.5385 | 17951922.0361
Total | 97773016.5508 | 90551488.7271 | 94162294.3143