Erection of Hotel & Conference Facility with Associated Access, Parking and Landscaping

CONSTRUCTION AND ENVIRONMENT MANAGEMENT PLAN

FOR

| Contract Name | Bicester Motion |
| --- | --- |
| Contract Address | Bicester Heritage Buckingham Road Launton Bicester OX26 5HA |
| Contract Number |  |
| Date Produced | April 2022 |

| CONTENTS |
| --- |
| Section 1.0 Section 2.0 |  | Scope of Work Contact Details |  |  |
| Section 3.0 |  | Site Comments |  |  |
| Section 4.0 |  | Traffic Arrangements |  |
|  | 4.1 4.2 | Site Access Site Fencing |  |
|  | 4.3 4.4 | Vehicle Movements on Site Loading and Unloading of Plant and Materials |  |
|  | 4.5 | Pedestrian Movements on Site |
|  | 4.6 | Vehicle/Pedestrian Segregation |  |
|  | 4.7 | Signage Requirements |  |
|  | 4.8 | Banksman requirements |  |
|  | 4.9 4.10 | Public Highway and Site Environment Maintenance Road Closures and Traffic Management |  |
| Section 5.0 |  | Responsibilities |  |
| Section 6.0 |  | Traffic Management Plan Drawing |  |
| Section 7.0 Section 8.0 Section 9.0 Section 10.0 Section 11.0 Section 12.0 |  | Site Logistics Plan – Access Plant Parking, Fuelling Station and Spill Kit Plan Site Compound Plan Waste Management Plan Area Plan Ecology |  |
| Revision Number | 0 | Date |  |
| Approved by | Date |
| Project Manager |  |  |
| Construction Director |  |  |
| HSEQ Advisor |  |  |

| Revision Number | Rev C | Date | 31 October 2022 |
| --- | --- | --- | --- |
| Approved by | Date |
| Project Manager |  |  |
| Construction Director |  |  |
| HSE Advisor |  |  |

Traffic Management Plan read and understood by:

| Name | Position | Date | Signature | Revision Number |
| --- | --- | --- | --- | --- |
| Jonty Ashworth | Development Director |  |  |  |
| Norman White | Snr Project Manager |  |  |  |
| Ben Tatton | Project Manager |  |  |  |

Introduction

This Construction Management Plan has been compiled by the Bicester Motion project management team to comply with the requirements of Construction Design and Management Regulations 2015 (CDM). The Plan forms the basis of traffic management on the site and is tailored to suit the project.

The plan is a “live document” to be supplemented and/or revised as the project develops by the introduction of supporting documents such as Sub-Contractor method statements, risk assessments or any documentation relevant to the safety, health and environment of the project

- Scope of Work

To undertake the construction of a Hotel and Conference facility with associated access, parking and landscaping The buildings and associated facilities are generally for use aparthotel for the purpose of Class C1 (Hotel use) as outliners in the Notice of Decision dated 11th March 2020 Site working hours: Monday – Friday 8am – 6pm Saturday 8am – 12:30pm Sunday No works without prior arrangement unless an emergency. Site traffic to arrive on site from 7am but no works to be undertaken until 8am unless of a priority nature which will not be audible from the site boundary. The Project is scheduled to commence on-site on the Mid-November 2022

No work is permitted on site on Public or Bank Holidays

- Contact Details

Contact details for the site staff are as follows:

Development Manager		Jonty Ashworth	01869 327928

Senior Project Manager		Norman White		01869 327928

Project Manager			Ben Tatton		01869 327928

- Site Comments

We will maintain a site comments book for use by the client, project team, local businesses and local residents.  This will be reviewed and actioned regularly and can be discussed at the monthly progress meetings.

- Traffic Arrangements

The final, approved Construction Phase Traffic Management Plan (CPTMP), part of the overall Construction Phase Health, Safety, Environment and Quality (HSEQ) Plan, will take full account of all site transport arrangements and local / existing traffic routes and movements.

The plan will be agreed with the Local Authority Highways Department prior to commencing main works on site and will consider and detail the following:

- We have considered the approaches to site and minimised any risks

- We understand the site requirements for the area surrounding the site

- The site entrance is off the A4421, Bicester Ring Road.

- The site is within close proximity of residential properties and other operational businesses.

  - Site Access

- Site access and egress routes together with signage demonstrating safe access to the site taking into account surrounding land use and adjacent buildings.  See sketch below

- Staff and visitor parking arrangements - No vehicles will be allowed to park on the approach roads to the site.  The site gateman will keep the approach roads under surveillance ensure that no vehicles associated with the site are parked on the approach roads.

- Arrangements and timing of deliveries to the site.  Major plant and equipment will be delivered to site generally between 09:30 and 16:30 hours.

- Any abnormal loads will have the delivery route approved by the Highways Agency prior to delivery.

- Arrangements for the removal of waste.

- Vehicle and plant and equipment movement - An adequate turning area will be provided always to ensure that as no vehicle reverse out of the entrances of the site

- Pedestrian Routes - Separate and dedicated pedestrian access routes and walkways will be provided around the site in order to provide safe access for site operatives and others around the site.

- Existing vehicular and pedestrian routes.

- Signage requirements.

- Banksman requirements for the co-ordination of movements into, around and off the site.

- Traffic plan drawings.

- Detailed methodology and designs will be submitted for approval prior to works commencing.

  - Site Fencing

Site fencing will be provided to the perimeter of the local site and the site compound.  This will be installed at the start of the main project works and will consist of heras fencing with an area of timber hoarding at the main site entrance.  Heras fencing, along with site signage and pedestrian fencing on-site will be regularly inspected and immediately repaired should it become necessary.

  - Vehicle Movements on Site

The following procedures / arrangements for will apply for traffic routes on site:

- All traffic and pedestrian routes will be clearly separated from each other by designated walkways, signage and suitable barriers.

- Road crossing points will be clearly identified using red barriers and signage within the pedestrian walkway fencing.

- Vehicles will be subject to a 5mph site speed limit.

- All major deliveries to site will be pre-booked onto site a minimum of 48hours notice and on arrival will notify security.

- All delivery vehicles will sign in and security will notify the respective contractor of their presence before releasing them onto site.

- All delivery drivers will be advised of site issues on arrival including all pedestrian routes, crossing points, etc.

- All traffic on site will be checked for cleanliness prior to leaving the site and if required, will pass through the jetwash before entering the public road.

  - Loading and Unloading of Plant and Materials

All offloading of plant and materials will be carried out on-site, generally within the site compound area off the A4421.  Deliveries and off-loading will be co-ordinated by the gateman using the 48 hour booking procedure.

Should the need arise to alter these arrangements this will be discussed fully with the client steering group, project team and local businesses and residents

  - Pedestrian Movements on Site

The following procedures / arrangements will apply for pedestrian routes on site:

- All traffic and pedestrian routes will be clearly separated from each other by designated walkways and suitable barriers.

- Road crossing points will be clearly identified with barriers and warning signage.

- Vehicles will be subject to a 5mph speed limit.

  - Vehicle/Pedestrian Segregation

As noted in 4.3 above

  - Signage Requirements

Regulation signage will be provided from the highway and throughout the clearly indicating site guidance for all users and visitors. Additional signage will be provided throughout the Bicester Motion site informing casual users of the site that site works are progressing.

  - Banksmen Requirements

A trained, qualified banksman will ensure vehicles enter and exit site safely without causing issues with pedestrians and vehicles.  While on-site vehicles will be restricted to non-pedestrian areas

  - Public Highway and Site Environment Maintenance

Prevention of dust, dirt, mud and debris on-site and on the surrounding roads will be managed by:

- Regular inspections and monitoring - The Project Manager, along with appointed main contractor site staff to agree appropriate road cleaning measures as necessary dependent on the climatic conditions.

- Reducing the number of vehicles leaving the site through adopting sustainable construction techniques which maximise the volume of suitable recoverable materials.

- Minimising the amount of mud generated on site by grading and maintaining site haul roads.

- Sheeting up of all lorries before leaving the site to prevent spillages of mud and debris.

- Having a road sweeper on call to clean and maintain the surrounding roads and footpaths and the site entrance weekly or at a greater frequency as site conditions dictate.

- Damping down in extended periods of dry weather.

- Inspecting and cleaning all vehicles leaving the site, ensuring that no vehicles leave site until their wheels, chassis, and external bodywork have been effectively cleaned and washed free of earth, mud, clay, gravel, stones or any other similar substance. We will provide, install and operate a suitable wheel”rate, for the duration of the Wc highwayen adjcant to the be fully trained to deliver excellent customer serviceuitable means

- d cleaning facility near the site entrance.

  - Road Closures and Traffic Management

It is unlikely that road closures will be required.  Should this prove necessary at any time it will be identified in good time and the client steering group, project team and Highways Department notified in sufficient time to allow the road closure to take place to suit the project programme.

There will not be a need for traffic management during the project works as all off-loading will be carried out within the confines of the site.

- Responsibilities

| Issue | Primary responsibility | Delegated to | Notes |
| --- | --- | --- | --- |
| 1. Traffic management | Project Manager | Site Manager | Daily visual inspection |
| 2. Traffic segregation | Project Manager | Site Manager | Daily visual inspection |
| 3. Traffic signage | Project Manager | Site Manager | Daily visual inspection |
| 4. Banksmen | Project Manager | Site Manager | Daily visual inspection |
| 5. Highway maintenance | Project Manager | Site Manager | Daily visual inspection |

- Traffic Management Plan Drawing

- Site Logistics Plan - Access

The plan below identifies our logistics proposals

- This will allow safe working.

- Site vehicular access will be via the A4221.

- Traffic will access the building footprint via the haul road turning into the footprint area in front of the work face.

- Signage and traffic management arrangements will be put in place to control the vehicles and to direct pedestrians to alternative entrances.

- Haul road will be constructed and maintained and kept clean always.

- Controlled hours for delivery periods will be set up with all suppliers in the pre - let meetings

- Construction vehicles to minimise risk to road users shall include sidebars, audible“ turn left“ warning and reversing beepers.

- Any changes to existing points of access shall have the sightlines approved by the local planning authority before use.

- Plant Parking, Fuelling Station and Spill Kit Plan

A dedicated individual will be delegated by the Project Manager to take overall responsibility to ensure that the environment is fully protected from any contamination. This will include the following:

- Ensuring all diesel tanks are doubled bunded and kept locked at all times.

- All items of plant are parked in a designated area for re-fuelling with drip trays or nappies sufficient for the task in hand.

- A fire call point will be established at the re-fuelling point with Co2 and foam extinguishers available.

- A register of all spill kits will be maintained in the Project Office and their locations will be clearly marked on a site plan.

- Training on environmental spills will be reviewed and updated as necessary, including key subcontract personnel

- Site Compound Plan

The plan below identifies the proposed site compound setup for this project;

- A site-specific plan will be developed and circulated to all relevant parties and clearly displayed on site.

- The site offices and car parking will be located within the site compound (see sketch below) providing an ideal location for safe access and enabling on-site queueing for vehicles where necessary. Turning within the site curtilage will be available

- Car parking for Staff and Visitors within this compound area will be provided and maintained.

- We will provide a contractor’s vehicle parking area within the office and welfare compound area site boundary and will relocate this as the project develops.

- A gatehouse with full time security is indicated to the right-hand side of the access (see sketch below).

- The plan below shows the indicative site office layout for this project.

- Waste Management

Segregated waste skips will be provided to ensure minimum 95% of waste is recycled to meet our sustainability responsibilities.  While some segregation can be carried out at site (plasterboard is a good example) the majority of waste segregation will be carried out off-site at the Waste Transfer Station and a report provided to confirm we have met this target.

Where possible demolition waste will be recycled on-site, being crushed and graded into sub-base material for use below slabs and roadways.

- Ecology

We refer to the BSG Ecology Survey Update of 2017 with reference to protected species:

  - Bats

Noted there was no potential for roosting at this site; short-mown grass also renders the area unsuitable as a foraging habitat

  - Badgers

Noted there are no signs of species at this site

  - Birds

There is potential for nesting birds to be present in the hedgerows to the West; these will not be disturbed during the nesting season (March-August inclusive)

# Text boxes

Site Car Park

Site Welfare

Gatehouse

Materials