Full Business Case (Stage 2 Commit to Construct)

| Project/Programme Name: | Christopher Rawlins CE (VA) Primary School – Expansion to 1.5FE |
| --- | --- |
| Total Capital Budget: | £2.442m |
| Divisions Affected: | Adderbury and Deddington |
| Purpose of this report: | This report requests approval and to contractually commit to construction of this project. |
| Approval No: | ED875 (WBS C.AE00914.01) |

Sign-off & Approval

In preparing this report input must be obtained from the following:

| Responsible Owner | Name | Date |
| --- | --- | --- |
| Service Manager/ Client / Project Sponsor (Contributor) | Kevin Griffin | 5/10/16 |
| Delivery Team Representative / Project Lead (Author) | Nick Tomkins | 6/10/16 |
| Service Finance Business Partner or Senior Financial Adviser (Contributor) |  |  |
| The Capital Finance Team (Contributor) | Graham Clare | 5/10/16 |
| Other Contributors as applicable (e.g. developer funding, asset strategy) |  |  |

Final approval as per the Financial Procedure Rules must be obtained from:

| Approval Level Required | Name | Date |
| --- | --- | --- |
| £2m to £5m - relevant Director and the Chief Finance Officer in consultation with the relevant Cabinet Member | Lorna Baxter / Chris McCarthy |  |
| Over £5m - Cabinet/ On behalf of Cabinet (Leader of the Council]) |  |  |

* In the case of Highways & Transport or Property projects the relevant Service Manager and Deputy Director are those responsible for delivery.

1	 Description & Objectives of the Proposal / Desired Outcomes & Business Benefits

Description and Objective

The provision of additional housing in the Deddington and Adderbury areas have resulted in the requirement for Christopher Rawlins CE (A) Primary School to expand from 1FE to 1.5FE.

The school falls under the control of the Oxford Diocese, but as the expansion is required to meet OCC’s Basic Need provision, funding is being provided through S106 contributions and the Corporate Resources (Basic Need).  This project will provide the necessary funding to facilitate the school expansion from 1FE to 1.5FE.

Business Benefits

The project will support the County Council meet its statutory duty to provide sufficient pupil places.

The project meets one of the three corporate priorities in the Oxfordshire County Council’s Corporate Plan 2016-2020:

•  	A strong and thriving economy

The project is in line with the 4 priorities in the Oxfordshire’s Children and Young People’s Plan 2015/18;

•	Ensuring children have a healthy start in life and stay healthy into adulthood

•	Narrowing the gap for our most disadvantaged and vulnerable groups

•	Keeping children and young people safe

•	Raising achievement for all children and young people

The project meets two of the 6 corporate principles for capital prioritisation:

Priority 1: projects which enable compliance with our legal & statutory duties, including projects which address any infrastructure deficits related to statutory compliance.

Priority 3: projects where a major proportion is funded from developer contributions, Community Infrastructure Levy, grant or revenue contributions.

The project meets one of the objectives in the Corporate Asset Management Plan 2015/15:

Objective 4: Put in place property that is fit for purpose and supports corporate priorities and service business strategies.

## 2	Updated Project Scope

The Outline Business Case for this proposal was approved on 14 March 2016 (see Appendix A).  Since then the project scope has not changed, with only minor internal design changes being agreed with the end user during a stakeholder design meeting.  These changes will improve the relationship between the Reception classroom and the Nursery classroom by opening up some of the dividing walls.

Requirements of the Planning Approval included providing a bicycle shelter and works to the highway to extend a parking layby.  These works have been incorporated and added to the project costs.

New Build Extensions providing:

- 2no. KS2 classrooms

- Staffroom

- Hall extension including hall storage

- 2no. Reception classrooms

- Part Nursery class

Internal Remodel & External Works providing:

- Replace hard play lost to new build

- Relocate adventure playground

- Remodel FS main entrance and FS external play area

- New Multi-Use Games Court (MUGA)

## 3	Estimated Cost & Proposed Funding Plan

The budget provision at the end of the feasibility stage (as approved in the OBC) was £2.446m, and the current cost estimate based on a confirmed tender price is £2.442m

This current cost is based on the tender return evaluation, dated 30 Sept 2016 (see Appendix B). The project cost build-up includes a costed risk register of £0.040m (see Appendix C), and a client contingency provision of £0.093m.

Summary of capital budget requirement:

|  | Stage 1 £000 | Stage 2 £000 |
| --- | --- | --- |
| A: Cost of feasibility and preliminary design (previously released at Stage 0b) | 0 | 0 |
| B: Estimated cost of detailed design, procurement & enabling works (previously released at stage 1) | 200 | 317 |
| C: Estimated delivery / construction cost (requested to be committed at stage 2) | 1,761 | 1,653 |
| D: Contingency | 134 | 93 |
| E: Irrecoverable VAT | 351 | 379 |
| Total | 2,446 | 2,442 |

The estimated annual expenditure profile for the project is as follows:

| Year | 2016/17 | 2017/18 | Contingency |
| --- | --- | --- | --- |
| £000 | 1,349 | 1,000 | 93 |

Funding

S106 resources are currently identified as £0.760m held with a further £0.568m secure, total of £1.328m. With indexation the overall forecasted total is £1.4m. The remaining funding gap of £1.042m will be initially funded from basic need.  As this project will provide the infrastructure to accommodate the forecast children within the catchment area and Deddington, the Developer Funding Team will seek future S106 contributions in respect of housing development which fall within the school’s admission number.

Ongoing Revenue Costs

The school will be responsible for any additional staff and for additional maintenance and running costs. The building will be more cost efficient to run due to benefits gained from the incorporation of the latest design technology for windows systems, lighting and insulation, which are aimed at minimising energy costs. These will need to be funded from the school’s delegated budget.

## 4	Project Delivery Timetable & Procurement Plan

Enabling works were carried out over the summer holiday to the kitchen to enable the school to deliver school meals during the main construction contract.  This element of work was approved in the OBC.

The main works will be split into 2 phases; phase 2a will extend the hall and create a new staffroom and provide 2 new classrooms.  Phase 2b will extend and remodel the Foundation Stage accommodation, and will make use of the 2 new classrooms created in Phase 2a to decant into, whilst the Foundation Stage accommodation is out of use.

The provision of additional classrooms in Phase 2a creates sufficient teaching accommodation for the school to take in 45 pupils into Reception in September 2017, even though Phase 2b is programmed to complete at the end of October 2017, thus removing the need to bring temporary classrooms onto the site.

The final works to the kitchen, to open it up fully and re-fit out, and the breaking through into the hall extension will be carried out over the 2017 summer holiday so that they will not impact on the daily operation of the school.

The anticipated construction delivery programme is:

| Activity | Start Date | Finish Date | Milestone/decision point & scheduled technical gateways |
| --- | --- | --- | --- |
| Enabling works incl fit-out | 25/7/16 | 26/8/16 |  |
| Main contract tender period | 25/7/16 | 8/9/16 |  |
| Stage 2 Gateway and FBC | 20/9/16 | 7/10/16 | FBC Approval |
| Mobilisation | 3/10/16 | 7/11/16 |  |
| Phase 2a construction | 7/11/16 | 1/5/17 | Phased PC |
| Phase 2b fit-out and relocation | 2/5/17 | 15/5/17 |  |
| Phase 2b construction | 15/5/17 | 6/11/17 |  |
| Phase 2b fit-out and relocation | 6/11/17 | 20/11/17 | PC |

## 5	Risks, Constraints, Dependencies and Exclusions

The key risks to the project (outside of standard construction risks) are:

| Description of areas or sources of risk and impact on project | Mitigation | Owner |
| --- | --- | --- |
| Programme: The phasing of the works indicates completion at the end of Oct 17, with the school expanding to 1.5FE (and taking in 45 pupils into Reception) from Sept 17. | The classrooms created in phase 2a will enable the school to take 45 into Reception, and therefore this can be managed | Diocese / School |

## 6	Communication & Consultation

CEF (School Organisation & Planning) undertook a public consultation exercise between 28/9/15 – 8/11/15 to seek views on the proposed expansion of the school.  On 19/11/15, the Governing Body unanimously proposed that the proposal for the school expansion plan should go ahead with its full support.

At the delegated decision meeting on 14/12/15; the Cabinet Member for Children Education and Families formally supported the proposed expansion of Christopher Rawlins School from 1FE to 1.5FE, with effect from September 2017.

Throughout the planning and design stages of the project, the proposals have been shared with the Head, Governors and FS staff, to ensure their continued support.  The project has the full support of the Oxford Diocese.

## 7	Project Governance

The project sponsor is Kevin Griffin from Children, Education & Families (CEF).

The Project Lead within Property & Facilities is Nick Tomkins, who has been working closely with the Headteacher, Oxford Diocese and their Consultants.

The project was reviewed at the Stage 2 Gateway on 20 September 16, after tenders had been received.  The proposals were deemed acceptable and suitable.

Subject to Full Business Case approval, the project will be delivered by the Oxford Diocese. A formal Funding Agreement has been drafted between the Diocese and OCC, and is in a position to be signed by both parties.

The project is part of the Basic Need Programme, which is governed by the Property Performance Delivery Group.

# 8	Supporting Documents

## Appendix A – Approved Outline Business Case

# Appendix B - Cost Plan

## Appendix C - Project Risk Register